## Project Planner
Sprint 2 - Accuracy
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Develop a plan (Gantt chart) | Maheen, Gina | 1 | 0.5 | 1 | 0.25 | 100%
Email Gantt Chart to Members | James | 1 | 0.25 | 1 | 0.25 | 100%
Github Repository | Gina | 1 | 0.25 | 1 | 0.25 | 100%
Make SDD Google Doc | Gina | 1 | 0.25 | 1 | 0.25 | 100%
Staffing Plan | All Members | 2 | 0.25 | 1 | 0.25 | 100%
Build requirements table | All Members | 2 | 0.5 | 2 | 0.5 | 100%
Requirements Sign off Table | All Members | 2 | 0.5 | 2 | 0.25 | 100%
Algorithm | All Members | 3 | 0.5 | 3 | 0.5 | 100%
Flow Chart | James | 4 | 1 | 4 | 0.5 | 100%
Block Code | Maheen | 5 | 1 | 4 | 0.5 | 100%
Test Block Code | Maheen, Gina | 6 | 2 | 5 | 2 | 100%
Sensor Data Diagram | Maheen | 8 | 0.5 | 7 | 0.5 | 100%
Test Table | Maheen, Gina | 9 | 1 | 8 | 1 | 100%
Robot Video | Gina | 10 | 1 | 9 | 2 | 100%
System Design Document | All Members | 11 | 5 | 11 | 2 | 100%